# PCSS II Multi-Club Platform: Technical Backlog

## Backlog Usage Notes

- Priority scale: P0 (must-have), P1 (high), P2 (important), P3 (nice-to-have)

- Effort scale: S (1-2 days), M (3-5 days), L (1-2 weeks), XL (2+ weeks)

- Each item includes acceptance criteria and dependencies.

---

## Epic A: Multi-Club Domain Model and Schema

### A1. Introduce organization and club entities

- Priority: P0

- Effort: L

- Owner: Platform/Architecture

- Description: Add explicit organization and club models with IDs, slugs, and metadata.

- Acceptance criteria:

- Organization and club structures exist in canonical schema.

- Club content references `clubId`.

- Existing Robotics content mapped to `clubId=robotics`.

- Dependencies: none.

### A2. Versioned schema contract

- Priority: P0

- Effort: M

- Owner: Platform

- Description: Add schema versioning and migration hooks.

- Acceptance criteria:

- `schemaVersion` required in config/content documents.

- Migration utility exists for old to new model.

- Validation fails gracefully with clear errors.

- Dependencies: A1.

### A3. Club type presets

- Priority: P1

- Effort: M

- Owner: Product + Platform

- Description: Define club presets for robotics, science, math, art, physics, biology.

- Acceptance criteria:

- Presets include default nav, modules, and copy placeholders.

- New club creation from preset is one command or admin action.

- Dependencies: A1, A2.

---

## Epic B: Layered Configuration Engine

### B1. Config layering implementation

- Priority: P0

- Effort: L

- Owner: Platform

- Description: Implement merge chain `platform -> org -> club -> env`.

- Acceptance criteria:

- Deterministic merge with tests.

- Primitive override and object deep merge rules documented.

- Dependencies: A1.

### B2. Runtime validation and safe fallback

- Priority: P0

- Effort: M

- Owner: Platform

- Description: Validate club configuration at load time and fail safely.

- Acceptance criteria:

- Invalid config does not crash entire app.

- Club-level error page includes diagnostic id.

- Other clubs remain available.

- Dependencies: B1.

### B3. Configuration diff tooling

- Priority: P2

- Effort: S

- Owner: Platform Tooling

- Description: Add config diff utility for review and approvals.

- Acceptance criteria:

- Human-readable diffs for org and club config changes.

- Dependencies: B1.

---

## Epic C: Routing and Tenant Resolution

### C1. Club resolver middleware

- Priority: P0

- Effort: M

- Owner: Frontend Platform

- Description: Resolve active club from route segment `/clubs/:clubSlug`.

- Acceptance criteria:

- Club slug selection works for all configured clubs.

- Invalid slug routes to club directory or controlled 404.

- Dependencies: A1.

### C2. Dynamic route generation per club

- Priority: P0

- Effort: L

- Owner: Frontend Platform

- Description: Generate routes from selected club’s page set.

- Acceptance criteria:

- Club pages are isolated and navigable.

- Existing robotics paths mapped/redirected as needed.

- Dependencies: C1, B1.

### C3. Umbrella pages and club directory

- Priority: P1

- Effort: M

- Owner: Frontend + Product

- Description: Add PCSS II pages listing all clubs and shared resources.

- Acceptance criteria:

- `/clubs` page lists active clubs and statuses.

- Dependencies: C1.

---

## Epic D: Reusable Section/Module System

### D1. Module contract spec

- Priority: P0

- Effort: M

- Owner: Frontend Architecture

- Description: Formalize module API (`moduleId`, `requiredConfig`, `defaultConfig`, variants).

- Acceptance criteria:

- Contract published in docs.

- Existing modules adapted to contract.

- Dependencies: A2.

### D2. Module registry and feature flags

- Priority: P0

- Effort: M

- Owner: Frontend Platform

- Description: Register modules by key and enable per-club via feature map.

- Acceptance criteria:

- Clubs can enable/disable modules without code edits.

- Dependencies: D1, B1.

### D3. Discipline variants

- Priority: P1

- Effort: L

- Owner: Frontend

- Description: Add variant support for event/program modules.

- Acceptance criteria:

- Robotics, science, and art can each render appropriate variant presentation.

- Dependencies: D2.

---

## Epic E: Branding and Theming

### E1. Tokenized theme model

- Priority: P0

- Effort: M

- Owner: Design Systems

- Description: Convert per-club branding to validated token sets.

- Acceptance criteria:

- Clubs can set primary/secondary/accent and typography tokens.

- Theme applies without CSS duplication.

- Dependencies: B1.

### E2. Accessibility validation for theme tokens

- Priority: P1

- Effort: M

- Owner: Design Systems + QA

- Description: Add contrast checks for configured token pairs.

- Acceptance criteria:

- Non-compliant combinations blocked in admin publish flow.

- Dependencies: E1.

### E3. Co-branding lockup

- Priority: P2

- Effort: S

- Owner: Design + Frontend

- Description: Support club-first and PCSS II endorsement placement rules.

- Acceptance criteria:

- Consistent co-brand footer/header patterns across clubs.

- Dependencies: E1.

---

## Epic F: Admin, RBAC, and Publishing Workflow

### F1. Role model and policy matrix

- Priority: P0

- Effort: M

- Owner: Platform + Security

- Description: Define and enforce org/club roles.

- Acceptance criteria:

- Roles: org-super-admin, org-editor, club-admin, club-editor, club-viewer.

- Access tests for each role pass.

- Dependencies: A1.

### F2. Club-scoped admin UI

- Priority: P0

- Effort: L

- Owner: Frontend

- Description: Admin supports selecting active club context.

- Acceptance criteria:

- Club admins only see/edit their club resources.

- Dependencies: F1, C1.

### F3. Draft/review/publish workflow

- Priority: P1

- Effort: L

- Owner: Product + Frontend

- Description: Introduce staged publishing with approvals.

- Acceptance criteria:

- Draft and published versions are separated.

- Publish action records approver and timestamp.

- Dependencies: F2.

### F4. Audit log and rollback

- Priority: P1

- Effort: M

- Owner: Platform

- Description: Record change history and support rollback snapshots.

- Acceptance criteria:

- Any publish can be rolled back by authorized roles.

- Dependencies: F3.

---

## Epic G: Performance and Reliability

### G1. Performance budgets and CI checks

- Priority: P0

- Effort: M

- Owner: Platform + QA

- Description: Add bundle/image budget checks in CI.

- Acceptance criteria:

- CI fails when budgets exceeded.

- Budget exceptions require justification.

- Dependencies: none.

### G2. Club-isolated error handling

- Priority: P0

- Effort: M

- Owner: Frontend Platform

- Description: Ensure bad config/content in one club does not impact others.

- Acceptance criteria:

- Synthetic test proves isolation behavior.

- Dependencies: B2.

### G3. Monitoring dashboards and alerts

- Priority: P1

- Effort: M

- Owner: SRE

- Description: Set per-club observability dimensions.

- Acceptance criteria:

- Dashboard by club for error rate, response time, and deploy health.

- Dependencies: C1.

---

## Epic H: Migration and Onboarding

### H1. Robotics migration to tenantized model

- Priority: P0

- Effort: M

- Owner: Migration Team

- Description: Move current site to club tenant model with no public regression.

- Acceptance criteria:

- Visual parity pass for existing robotics pages.

- Dependencies: C2, D2.

### H2. Science and Math onboarding

- Priority: P0

- Effort: M

- Owner: Migration Team

- Description: Launch first two non-robotics clubs from presets.

- Acceptance criteria:

- Both clubs deployed with independent branding and content.

- Dependencies: H1, A3.

### H3. Art, Physics, Biology onboarding

- Priority: P1

- Effort: L

- Owner: Migration Team

- Description: Launch next three clubs with variant module support.

- Acceptance criteria:

- All clubs can publish events and updates independently.

- Dependencies: H2, D3.

---

## Epic I: Documentation and Enablement

### I1. Platform handbook

- Priority: P0

- Effort: M

- Owner: Platform PM

- Description: Publish architecture, governance, and troubleshooting docs.

- Acceptance criteria:

- Playbook for onboarding and incident response available.

- Dependencies: A1 through H1 baseline.

### I2. Club admin training material

- Priority: P1

- Effort: S

- Owner: Product Ops

- Description: Produce quickstart guides for club editors/admins.

- Acceptance criteria:

- Club leads can publish content without engineering support.

- Dependencies: F2.

---

## Milestone Plan

### Milestone M1 (Weeks 1-3)

- A1, A2, B1, C1, D1, F1

### Milestone M2 (Weeks 4-6)

- C2, D2, E1, F2, G1, H1

### Milestone M3 (Weeks 7-9)

- H2, F3, F4, E2, G2

### Milestone M4 (Weeks 10-12)

- H3, C3, G3, I1, I2

---

## Definition of Done (Program Level)

1. Robotics, Science, Math, Art, Physics, and Biology run on one platform.

2. New club onboarding requires configuration only for standard scenarios.

3. Role enforcement and audit logging are active.

4. Performance budgets and reliability checks are enforced in CI.

5. PCSS II governance and operating handbooks are complete.

---

## Suggested Jira Structure

- Program: PCSS-II-CLUB-PLATFORM

- Epics: A through I (above)

- Stories: each backlog item (A1, A2, ..., I2)

- Labels:

- `multi-club`

- `umbrella-governance`

- `config-engine`

- `rbac`

- `migration`

- `performance`

---

## Resourcing Recommendation

Minimum cross-functional team:

- 1 Platform architect

- 2 Frontend engineers

- 1 Full-stack/platform engineer

- 1 QA automation engineer

- 1 Product/program lead

- Shared design support (part-time)

This staffing is sufficient to execute M1-M4 in a 10-12 week window with controlled risk.